## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Coy | Cori | Anna | Daylan | Feng | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | Coy | 12 |  | 2 |  | 2 | 0 |  |  |  | 2
| Requirements |  |  |  |  | 9 |  | 9 | [5 empty] | 0
|  | Gather | Requirements Engineer | Coy, Cori, Daylan, Feng, Anna | 2 |  | 3 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3
|  | Analyze | Requirements Engineer | Coy, Cori, Daylan, Feng, Anna | 4 |  | 3 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3
|  | Specify | Requirements Engineer | Coy, Cori, Daylan, Feng, Anna | 3 |  | 3 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3
| Documentation |  |  |  |  | 30 |  | 34 | [5 empty] | 0
|  | Project Charter | Manager, Devloper | Coy, Cori, Daylan, Feng, Anna | 2 |  | 5 |  | 1 | 1 | 1 | 1 | 1 | 5
|  | Release Plan | Project Manager | TBA | 4 | [8 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Coy, Cori, Daylan, Feng, Anna | 5 |  | 10 |  | 2 | 2 | 2 | 2 | 2 | 10
|  | Project Plan | Project Manager, Developers | Coy, Cori, Daylan, Feng, Anna | 5 |  | 5 |  | 1 | 1 | 1 | 1 | 1 | 5
|  | Architecture Document | Architect | Coy | 4 |  | 4 |  | 4 |  |  |  |  | 4
|  | Test Report | Tester | Feng | 8 |  | 8 | [5 empty] | 8 | 8
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Daylan, Cori | 2 |  | 2 |  |  | 1 |  | 1 |  | 2
Coding
Iteration 1: | Development |  |  |  |  | 10.5 |  | 10.5 | [5 empty] | 0
|  | Determine technology needs | Developer | Coy, Cori, Daylan, Feng, Anna | 3 |  | 3 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3
|  | Research new langauge/framework (Django) | Developer | Cori, Daylan Feng, Anna | 5 |  | 5 |  |  | 1.25 | 1.25 | 1.25 | 1.25 | 5
|  | Get Django admin running | Project Manager | Coy | 2 |  | 2 |  | 2 |  |  |  |  | 2
|  | Write basic proxy code | Project Manager | Coy | 0.5 |  | 0.5 |  | 0.5 |  |  |  |  | 0.5
|  | Research deployment methods | Project Manager | Coy | 0 |  | 0 |  | 0 |  |  |  |  | 0
| Analysis |  |  |  |  | 1 |  | 1 | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Coy, Cori, Daylan, Feng, Anna | 1 |  | 1 |  | 1 |  |  |  |  | 1
Total | [5 empty] | 62.5 |  | 56.5 | 15.9 | 8.65 | 7.65 | 8.65 | 15.65 | 56.5
Iteration 2: | Design |  |  |  |  | 7 |  | 7
|  | Implement any design changes | Project Manager, devloper | Coy, Daylan | 2 |  | 2 |  | 1 |  |  | 1 |  | 2
|  | Risk analysis | Developer | Feng | 2 |  | 2 | [5 empty] | 2 | 2
|  | UI Design modeling | Developer | Cori | 3 |  | 3 |  |  | 3 |  |  |  | 3
| Development |  |  |  |  | 21 |  | 16
|  | Review requirements | Project manager, Devloper | Coy, Cori, Daylan, Feng, Anna | 2 |  | 2 |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2
|  | Design Django models and DB | Project manager, Devloper | Cori, Anna, Coy | 8 |  | 6 |  | 2 | 2 | 2 |  |  | 6
|  | Handle sample data | Developer | Cori, Anna | 3 |  | 3 |  | 1.5 |  | 1.5 |  |  | 3
|  | Implement UI | Developer | Coy, Daylan | 8 |  | 5 |  | 2.5 |  |  | 2.5 |  | 5
| Analysis |  |  |  |  | 6.5 |  | 5
|  | System Testing | Developer, Tester | Daylan, Feng | 2 |  | 2 |  |  |  |  | 1 | 1 | 2
|  | Bug fix as required | Tester, Developer | Cori, Feng Daylan, Anna | 2 |  | 2 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Evaluate needs for next iteration | Project Manager | Coy | 2.5 |  | 1 |  | 1 |  |  |  |  | 1
Total | [5 empty] | 34.5 |  | 28 | 8.4 | 5.9 | 4.4 | 5.4 | 3.9 | 28
Iteration 3: | Design |  |  |  |  | 6 |  | 5
|  | Implement any design changes | Devloper | Daylan | 2 |  | 1 |  |  |  |  | 1 |  | 1
|  | Risk analysis | Developer | Feng | 2 |  | 2 | [5 empty] | 2 | 2
|  | UI design modleing/sotryboarding | Developer | Cori, Daylan | 2 |  | 2 |  | 1 |  |  | 1 |  | 2
| Development |  |  |  |  | 33 |  | 29
|  | Review requirements | Project manager, Devloper | Coy, Cori, Daylan, Feng, Anna | 6 |  | 6 |  | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 6
|  | Create functionality between front/back end | Project manager, Devloper | Cori, Anna, Coy | 16 |  | 12 |  | 4 | 4 | 4 |  |  | 12
|  | Handle sample data | Developer | Cori, Anna, Coy | 3 |  | 3 |  | 1 | 1 | 1 |  |  | 3
|  | Implement UI | Developer | Daylan | 8 |  | 8 |  |  |  |  | 8 |  | 8
| Analysis |  |  |  |  | 6.5 |  | 5
|  | System Testing | Developer, Tester | Daylan, Feng | 2 |  | 2 |  |  |  |  | 1 | 1 | 2
|  | Bug fix as required | Tester, Developer | Coy, Cori, Daylan, Feng, Anna | 2 |  | 2 |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2
|  | Evaluate needs for next iteration | Project Manager | Coy | 2.5 |  | 1 |  | 1 |  |  |  |  | 1
Total |  |  |  |  | 71 | 86.5 | 1 | 39 | 8.6 | 6.6 | 6.6 | 12.6 | 4.6 | 39